## Milestone
UNIFIND DNTU - MILESTONE
Plan vs Actual - cập nhật theo sprint
ID | Milestone | Start | End | Deliverable | Owner | Status | Plan % | Actual %
M01 | Sprint 1 - Analysis & UI | 2026-09-15 | 2026-09-28 | Requirement, mockup, architecture draft, starter | Phạm Đình Bảo | In Progress | 100 | 65
M02 | Sprint 2 - Core Platform | 2026-09-29 | 2026-10-19 | Auth/RBAC, DB, Item CRUD, Search | Phạm Đình Bảo | Planned | 100 | 0
M03 | Sprint 3 - Matching & Claim | 2026-10-20 | 2026-11-16 | Matching, Claim, Staff, Notifications | Phạm Đình Bảo | Planned | 100 | 0
M04 | Sprint 4 - Admin & Quality | 2026-11-17 | 2026-12-07 | Admin, reports, regression, hardening | Phạm Đình Bảo | Planned | 100 | 0
M05 | Finalization | 2026-12-08 | 2026-12-20 | UAT, deploy, docs, final demo | Phạm Đình Bảo | Planned | 100 | 0